## Sheet1
Task No. | Owner | Rubric Item | Measurable Task | Evidence Required in Notebook | Definition of Done | Internal Deadline | Marks | Contribution % | Status
1 | Nour | Task 2: Code | Implement load_data(path) to load the flower image dataset | Output showing image array shape, label array shape, class names, and number of images per class | All image data and labels load correctly with no errors | 18-21 MAY | 1 | 2.5% | Not started
2 | Nour | Task 3a: Code | Implement split_data(X, Y, train_fraction, randomize=False, eval_set=True) | Output showing train, validation, and test set sizes | Function returns correct split datasets in the expected structure | 18-21 MAY | 1 | 2.5% | Not started
3 | Nour | Task 3b: Report | Explain the split strategy and class balance | Markdown explanation plus class distribution table for train/validation/test | Explanation clearly justifies that the split is reasonable and does not introduce class imbalance | 27-29 MAY | 2 | 5% | Not started
4 | Nour | Task 4: Code | Implement load_model() using pretrained MobileNetV2 from tf.keras.applications | Model summary or printed confirmation showing MobileNetV2 loaded correctly | Function returns the pretrained MobileNetV2 model and is ready for transfer learning | 18-21 MAY | 2 | 5% | Not started
5 | Nour | Task 5: Code | Replace/add the final classifier layer for the 5 flower classes | Model summary showing final output layer has 5 outputs | Model architecture is valid for classifying daisy, dandelion, roses, sunflowers, and tulips | 18-21 MAY | 4 | 10% | Not started
6 | Nour | Task 6b: Report | Explain how transfer_learning() works | Markdown explanation of frozen MobileNetV2 layers, classifier head, compile step, and training step | Reader can understand the function workflow without needing to decode the whole function | 27-29 MAY | 1 | 2.5% | Not started
7 | Nour | Task 14: Report | Write the final technical conclusion | Markdown conclusion recommending learning rate, momentum, model approach, limitations, and future work | Conclusion references actual experiment results from the notebook | 27-29 MAY | 1 | 2.5% | Not started
| Total | [5 empty] | 12 | 30%
8 | Joshua Oates | Task 6a: Code | Implement baseline transfer_learning() training using SGD | Training output/history using learning_rate=0.01, momentum=0.0, nesterov=False | Baseline model trains successfully and returns usable history/results | 21-24 MAY | 2 | 5% | Not started
9 | Joshua Oates | Task 7a: Code | Plot training and validation accuracy/error for standard transfer learning | Accuracy and loss/error plots with labels, legends, and titles | Plots are readable and clearly show training vs validation behaviour | 21-24 MAY | 2 | 5% | Not started
10 | Joshua Oates | Task 7b: Report | Interpret the baseline training plots | Markdown comment on learning trend, overfitting/underfitting, and validation behaviour | Comment directly refers to the plotted results | 27-29 MAY | 1 | 2.5% | Not started
11 | Joshua Oates | Task 8a: Code | Run 3 learning-rate experiments across different orders of magnitude | Results table/plot for 3 learning rates, e.g. 0.1, 0.01, 0.001 | All three learning-rate runs complete and are comparable | 21-24 MAY | 2 | 5% | Not started
12 | Joshua Oates | Task 8b: Report | Discuss learning-rate experiment results | Markdown comparison of the 3 learning rates | Best learning rate is clearly selected using evidence from results | 27-29 MAY | 2 | 5% | Not started
13 | Joshua Oates | Task 9: Code | Evaluate best learning-rate model on the test set and generate confusion matrix | Confusion matrix with class labels | Confusion matrix displays correct and incorrect predictions for all 5 classes | 21-24 MAY | 2 | 5% | Not started
14 | Joshua Oates | Task 10b: Report | Interpret confusion matrix and classification results | Markdown comment identifying strongest classes, weakest classes, and confusion patterns | Interpretation is specific to the displayed test results | 27-29 MAY | 1 | 2.5% | Not started
| Total | [5 empty] | 12 | 30%
15 | Joshua George | Task 10a: Code | Compute precision, recall, and F1 score using the best model | Metrics table for each class plus macro/weighted averages if possible | Precision, recall, and F1 are correctly displayed for the test set | 25-27 MAY | 2 | 5% | Not started
16 | Joshua George | Task 11a: Code | Implement and run k-fold validation with k=3 and two other k values | Results table showing metric averages for each k value | K-fold validation runs successfully and produces comparable results | 25-27 MAY | 2 | 5% | Not started
17 | Joshua George | Task 11b: Report | Compare k-fold results against the previous train/test split | Markdown comparison of k-fold stability vs earlier test result | Comment explains whether model performance is stable or split-sensitive | 27-29 MAY | 1 | 2.5% | Not started
18 | Joshua George | Task 12a: Code | Test 3 non-zero momentum values using the best learning rate | Results table/plot comparing 3 momentum values | All 3 momentum experiments run and are comparable | 25-27 MAY | 1 | 2.5% | Not started
19 | Joshua George | Task 12b: Report | Discuss how momentum changed training behaviour/results | Markdown explanation of whether momentum improved, worsened, or destabilised training | Best momentum value is selected or rejected using evidence | 27-29 MAY | 1 | 2.5% | Not started
20 | Joshua George | Task 13a: Code | Implement accelerated_learning() using precomputed frozen features F(x) | Feature extraction output, accelerated training results, and working accelerated_learning() function | Function avoids recalculating frozen MobileNetV2 features every epoch and produces valid training results | 25-27 MAY | 4 | 10% | Not started
21 | Joshua George | Task 13b: Report | Compare accelerated transfer learning against standard transfer learning | Plot/table comparing accuracy, loss, and/or training time | Discussion explains whether accelerated learning was faster and whether performance changed | 27-29 MAY | 2 | 5% | Not started
22 | Joshua George | Task 15: Groupwork | Write final contribution breakdown for all members | Contribution table/paragraph naming each person’s specific code/report contributions | Breakdown aligns with each person’s individual Section 2.1 report | 25-27 MAY | 3 | 7.5% | Not started
| Total | [5 empty] | 16 | 40%
Essential Unmarked Tasks
No. | Owner | Task | Measurable Output |  |  | Deadline |  |  | Status
23 | All members | Complete my_team() and confirm names/student numbers | my_team() returns all group members correctly |  |  | 2026-05-20 |  |  | Not started
24 | All members | Notebook integration check | All sections are in the correct order under clear task headings |  |  | TBD |  |  | Not started
25 | All members | Clean run test | Notebook runs top-to-bottom without missing variables, broken paths, or hidden dependencies |  |  | 2026-05-26 |  |  | Not started
26 | Submitter + all members | Final Canvas submission check | One person submits; all members verify the uploaded file is correct |  |  | 2026-05-29 |  |  | Not started